## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2231-swen-261-7-g cookierun
Testing Team Name | fill in when doing cross-team testing
/

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a helper I want to see a list of needs so that I choose what to contribute to. | Given that I am on the u-fund site when I am not on the Needs page then I must see a means to navigate to the Needs page. | Pass | GM; 3-31-26 | Pass | GM; 3-31-26
| Given that I am not on the Needs page when I choose the Needs page then I am taken to the Needs page. | Pass | GM; 3-31-26 | Pass | GM; 3-31-26
| Given that I am on the Needs page when there are no needs in the cupboard I see a message indicating that that there are no needs available to contribute. | Fail | GM; 3-31-26 | Pass | AG; 4-5-26
| Given that I am on the Needs page when there are needs in the cupboard then I see each need and short description. | Pass | GM; 3-31-26 | Pass | GM; 3-31-26
| Given that I am on the Needs page when there are needs in the cupboard then I see a means to add each need to my funding basket. | Pass | GM; 3-31-26 | Pass | GM; 3-31-26
As a Developer I want to submit a request to delete a single need SO THAT it is no longer in the cupboard | Given I am a manager for a need when I view the need then I expect to be able to remove it. | Fail | GM; 3-31-26, can not delete from ui yet | Pass | AG; 4-5-26
As a User I want to have my account be secure so that no one else can access my account. | Given that I do not have the username and password for an account I should not be able to access it | Fail | GM; 3-31-26, can access other accounts by editing urls | Pass | AG; 4-5-26
As a USER I want to be able to create/setup a new basic campaign so that i can get fundrasing for a cause/need | Given the user selects to create a campaign when the page loads then they expect to see a form with fields for information needed | Fail | Sprint 3 | Pass | AG; 4-5-26
| Given the user fills in all required fields correctly when they submit the form then they expect the campaign to be successfully created | Fail | Sprint 3 | Pass | AG; 4-5-26
| Given the campaign is successfully created when the process completes then they expect to see a confirmation message | Fail | Sprint 3 | Pass | AG; 4-5-26
As a User I want to upload images or videos so my campaign looks credible and engaging. | Given I am a manager when I upload media then I expect it to be stored. | Fail | Sprint 3 | Fail | Sprint 4
| Given I am a manager when I view my need then I expect it to be able to upload media. | Fail | Sprint 3 | Fail | Sprint 4
As a Developer I want to submit a request to delete a single need SO THAT it is no longer in the cupboard | Given I am a manager for a need when I view the need then I expect to be able to remove it. | Fail | Sprint 3 | Pass | AG; 4-5-26
As a Developer I want to submit a request to delete a single need SO THAT it is no longer in the cupboard | Given I am a helper when I look for a need / campaign then I expect to be able to see the details. | Fail | Sprint 3 | Pass | AG; 4-5-26